## Issue Management Log
WHS Issues Management Log
Number | Date & Time of Issue/ Reporting | Issue/Hazard | Description of issue | Location of issue | Impacted Individuals and Contact Details | Impact | Priority | Status | Owner | Control/ Actions planned | Resolution of control and date resolved | Has control worked? Is escalation required?
1 | 21/03/2021 3:00PM | Collection of backpacks on gym floor by doors | Members are bringing their bags on the gym floor whilst training, blocking acess to supplies cupboard. There are currently not enough lockers available to support the busy periods of the gym. | Gym Floor - ALL | N/A | Potential of trips, falls, sprains, strains, or broken bones. Unable to access supplies cupboard. | High | Closed | WHS Officer, Gym Manager | 1. Place signage to inform gym users to place their bags in a safe and secure area 2.Source and provide more locker access to gym users to support the busy periods. | 1. Additional signage placed around gym 21/03/2021 2. Purchase additional lockers 23/03/2021 3. Post consultation with WHS Committee | Yes control has worked. 1. Signage has been placed in visable areas of the gym 2. Lockers now suitably support the needs of the gym users. Escalation is not required
2 | 23/03/2021 8:00AM | Equipment not functioning | Some exercise bikes not working/ not working properly. | Bike Room 1 | N/A | Members using equipment and it malfunctions- injury incident potential | Medium | Closed | WHS Officer, Gym Manager | 1.Place signage on equipment indicating machine out of order / awating maintenance. 2.Book technican to assess and repair/replace equipment | 1. New signage placed on out of order equipment 24/3/2021 2. Technician booked for 30/03/2021 | Yes control has worked. 1. Signage has been placed on relevent equipment 2. Technican has repaired equipment. Escalation is not required
3 | 24/04/2021 2:40PM | Equipment not put away | Gym member (Lauren Georges) tripped over equipment left out and twisted ankle. | Cardio Room 2 | Lauren Georges 0411 333 444 Witness Alex Williams 0455 455 455 | Futher injuries or illnesses | High | Open | WHS Officer, Gym Manager | 1. Put equipment away immediately . 2.Place additional signage for staff and members to remind them to put equipment back in correct location. 3. Ensure all staff are aware of their responsibility to ensure equipment is stored safely and in accordance with WHS requirements. | 1. Equipment put away within 15 minutes of the issue being identified by the Trainer 24/04/2021. 2. Additional signage placed within an hour of the issue being identified 24/04/2021. 3. Discussed with all staff the importance of ensuring equipment is stored safely and in accordance with Bounce Fitness and WHS requirement. 24/04/2021 | No escalation required.
4 | 24/04/2021 10:00AM | Unclean equipment | Staff member (Sophie Davies) presents with rash on palms suspected to be linked to unclean gym equipment. | N/A | Sophie Davies 0400 999 777 | Potential spread of disease or infection | High | Open | WHS Officer | 1. Clean all gym equipment as per cleaning requirements. 2. Ensure all staff are aware of their responsibility to ensure gym WHS and hygiene requirements are followed. | 1. All quipment cleaned as per cleaning requirements within 24 hours of issue being raised 24/04/2021 2. Discussed with all staff the importance of ensuring that Bounce Fitness WHS and hygiene requirements are followed 24/04/2021 | No escalation required.
5 | 30/04/2021 9:15AM | Cleaning equipment not available | No cleaning liquids or cloths available to clean equipment after use. | Storage | N/A | Potential spread of disease or infection | Medium | Open | WHS Officer | 1.Place equipment in the gym to enable members and staff to clean equipment between uses. | 1. Cleaning equipment and supplies now placed at entrance of gym 30/04/2021 | No escalation required.
6 | 5/05/2021 11:30AM | Staff not adhering to WHS legislation and Bounce Fitness WHS policies and procedures | Complaints from gym members and staff that staff members are not following WHS legislation or Bounce Fitness WHS policies and procedures. | N/A | ALL Staff | Potential injuries and illnesses to staff and gym members | Medium | Open | WHS Officer | Enter response here | Enter response here | Enter response here