## Project Schedule
This document is Project Schedule.
It is part of the supporting assessment resources for Assessment Task 3 of BSBPMG532.
Week beginning
|  |  |  | Calendar | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-05 | 2020-09-12 | 2020-09-19 | 2020-09-26 | 2020-10-02 | 2020-10-09 | 2020-10-16 | 2020-10-23 | 2020-10-30 | 2020-11-06 | 2020-11-13 | 2020-11-20 | 2020-11-27
| Item | Topic | Activity | Responsible
Project start | bar: 2020-06-01
| 1 | Contract website developer
| 1.1 | Contract | Contact potential website developers | Project Manager | bar: 2020-06-01 to 2020-06-08
| 1.2 | Contract | Ask for quotes | Project Manager | bar: 2020-06-15 to 2020-06-22
| 1.3 | Contract | Review quotes | Project Manager | bar: 2020-06-15 to 2020-06-22
| 1.4 | Contract | Select most suitable quote | Project Manager | bar: 2020-06-22 to 2020-06-29
| 1.5 | Contract | Send contract to selected developer | Project Manager | bar: 2020-06-29
| 1.6 | Contract | Signed contract returned and file | Project Manager | bar: 2020-07-06
| 2 | Web site development
| 2.1 | Development | Set up initial meeting for discussion about web site | Project Team | bar: 2020-07-13 to 2020-07-20
| 2.2 | Development | Confirm brief in writing | Project Team | bar: 2020-07-27
| 2.3 | Development | Develop content | Project Team | bar: 2020-08-03 to 2020-08-24
| 2.4 | Development | Weekly meetings to discuss progress | Project Team | bar: 2020-08-31
| 2.5 | Development | Final meeting to review | Project Team | bar: 2020-08-31
| 2.6 | Development | Final changes sent by email | Project Team | bar: 2020-08-31
| 2.7 | Development | Provide bank details for shopping cart | Project Team
| 3 | Website sign off
| 3.1 | Marketing | Final meeting to review | Project Team | bar: 2020-09-05
| 3.2 | Marketing | Final changes sent by email | Project Team | bar: 2020-09-05
| 3.3 | Marketing | Test web site for functionality | Project Team | bar: 2020-09-12
| 3.4 | Marketing | Web site goes live | Project Team | bar: 2020-09-19 to 2020-09-26
| 4 | Training
| 4.1 | Training | Identify and document training needs | Project Manager | bar: 2020-09-19 to 2020-10-02
| 4.2 | Training | Develop suggested program for training | Project Manager | bar: 2020-09-19 to 2020-10-02
| 4.3 | Training | Organise training | Project Manager | bar: 2020-09-19 to 2020-10-02
| 4.4 | Registration | Implement training | Website developer | bar: 2020-10-02 to 2020-10-16
| 4.5 | Registration | Evaluate training | Project Manger | bar: 2020-10-16 to 2020-10-23
| 5 | Project completion
| 5.1 | Completion | Evaluation meeting | Project Team | bar: 2020-10-23 to 2020-10-30
| 5.2 | Completion | Lesson learned report and action | Project Team | bar: 2020-10-23 to 2020-10-30
| 5.3 | Completion | Action plan implemented | Project Team | bar: 2020-10-30 to 2020-11-13
Assessor instructions:
Students must update the website development section for the delay in one week.
Students must update section 3, 4 and 5 by one week.
Students must save the file name as Project Schedule_dd.mm.yy
Changes identified in red